## Doc_Submittals
Target Document | Submitted by | Submitted on | Done? | Incorporated On | Original Document Name | Other Comments | Drop Down List of Documents
Auxiliiary Programs | Mike Witte | 2012-09-23 | X | 2012-09-25 | DocSubmissions\AuxiliaryPrograms-HVACTemplate-MJW-2012-09-24.docx |  | Acknowledgements
Auxiliiary Programs | Jason Glazer | 2012-09-28 | X | 2012-09-28 | DocSubmissions\GettingStarted-EP-Launch-Threads.docx |  | Auxiliiary Programs
EngRef | RR/Linda Lawrie | 2011-10-20 | X | 2012-09-25 | DocSubmissions\Fig248-ZoneOAUnit.jpg | Still under discussion - RR/BG. | Compliance
EngRef | Brent Griffith | 2012-07-13 | X | 2012-09-24 | DocSubmissions\EngineeringReference_PVAV_Ratings.docx |  | EMS App Guide
EngRef | Chandan Sharma | 2012-08-01 | X | 2012-09-24 | DocSubmissions\EngRef_EnhanceSAMsforZoneComps_01Aug2012.docx |  | EngRef
EngRef | Bereket Nigusse | 2012-08-02 | X | 2012-09-25 | DocSubmissions\EngRef_StandardRatings_PhaseIV.docx |  | External App Guide
EngRef | Brent Griffith | 2012-08-08 | X | 2012-09-24 | DocSubmissions\EngRef_NoSimpleCondFD.docx |  | Getting Started
EngRef | Rich Raustad | 2012-08-23 | X | 2012-09-24 | DocSubmissions\EngRef_VRFHeatPumps_Aug22_2012.docx | had chart - had to convert to picture | Interface Dev Guide
EngRef | Heejin Cho | 2012-08-27 | X | 2012-09-24 | DocSubmissions\EngRef DetermineSystemAirFlowRate.docx |  | IORef
EngRef | Brent Griffith | 2012-09-05 | X | 2012-09-24 | DocSubmissions\EngRef_CR8252_Hc_out.docx |  | Mod Dev Guide
EngRef | Mike Witte | 2012-09-07 | X | 2012-09-24 | DocSubmissions\EngineeringReference-CR8965-MJW-2012-09-07b.docx | CR8695 | Output Details
EngRef | Bo Shen | 2012-09-12 | X | 2012-09-24 | DocSubmissions\VSASDXCoils_EngineeringReference.docx |  | Programming Standard
EngRef | Brent Griffith | 2012-09-19 | X | 2012-09-24 | DocSubmissions\EngRef_CR8842.docx |  | Tips & Tricks
External App Guide | Thierry Noudui | 2012-09-17 | X | 2012-09-18 | DocSubmissions\ExternalInterfaces_Application_GuideUpdate2.docx
Getting Started | Jason Glazer | 2012-09-28 | X | 2012-09-28 | DocSubmissions\GettingStarted-EP-Launch-Threads.docx
IORef | David Sailor | 2012-06-27 | X | 2012-06-27 | DocSubmissions\Material-RoofVegetation_DJS.docx
IORef | Brent Griffith | 2012-07-13 | X | 2012-09-10 | DocSubmissions\InputOutputReference_PVAV_Ratings.docx
IORef | Chandan Sharma | 2012-08-01 | X | 2012-09-10 | DocSubmissions\IORef_EnhanceSAMsforZoneComps_01Aug2012.docx
IORef | Bereket Nigusse | 2012-08-02 | X | 2012-09-10 | DocSubmissions\IORef_StandardRatings_PhaseIV.docx
IORef | Tianzhen Hong | 2012-08-03 | X | 2012-09-10 | DocSubmissions\IORef - CR8911.docx | CR8911
IORef | Brent Griffith | 2012-08-08 | X | 2012-09-10 | DocSubmissions\IO_Ref_SurfaceSpecificHeatTransferAlgo.docx
IORef | Simon Vidanovic | 2012-08-14 | X | 2012-09-10 | DocSubmissions\InputOutputReference_BSDF.docx
IORef | Rick Strand | 2012-08-14 | X | 2012-09-10 | DocSubmissions\20120814DetIceStorage.doc
IORef | Brent Griffith | 2012-08-22 | X | 2012-09-10 | DocSubmissions\IO_Ref_CR8186DaylightAvail.docx | CR8186
IORef | Rich Raustad | 2012-08-23 | X | 2012-09-10 | DocSubmissions\IORef_GroupVRF_21Aug2012.docx
IORef | Rich Raustad | 2012-08-23 | X | 2012-09-12 | DocSubmissions\IORef_ZoneHVACTerminalUnitVRF_21Aug2012.docx
IORef | Rich Raustad | 2012-08-23 | X | 2012-09-12 | DocSubmissions\IORef_GroupDesignObjects_23Aug2012.docx
IORef | Heejin Cho | 2012-08-24 | X | 2012-09-12 | DocSubmissions\IORef DetermineSystemAirFlowRate.docx
IORef | Mike Witte | 2012-08-28 | X | 2012-09-12 | DocSubmissions\InputOutputReference-MJW-Ticket6334.docx
IORef | Brent Griffith | 2012-08-30 | X | 2012-09-12 | DocSubmissions\IO_Ref_CR8112.docx | CR8112
IORef | Therese Stovall | 2012-09-06 | X | 2012-09-12 | DocSubmissions\InputOutputReferenceZoneEquip2012section.docx
IORef | Brent Griffith | 2012-09-10 | X | 2012-09-12 | DocSubmissions\IORef_CR8119_8191_Meters.docx
IORef | Brent Griffith | 2012-09-10 | X | 2012-09-12 | DocSubmissions\IORef_CR8970_BranchControl.docx
IORef | Brent Griffith | 2012-09-10 | X | 2012-09-12 | DocSubmissions\IORef_CR8445_WaterWelloutputs.docx
IORef | Brent Griffith | 2012-09-10 | X | 2012-09-12 | DocSubmissions\IORef_CR8652_convergencelimits.docx
IORef | Rich Raustad | 2012-09-10 | X | 2012-09-12 | DocSubmissions\IORefDXHeatingSingleSpeed_10Sep2012.docx
IORef | Mike Witte | 2012-09-11 | X | 2012-09-12 | DocSubmissions\InputOutputReference-Ticket6394-MJW-2012-09-11.docx
IORef | Bo Shen | 2012-09-12 | X | 2012-09-12 | DocSubmissions\VSASDXCoils_InputOutputReference.docx | incomplete?
IORef | Heejin Cho | 2012-09-13 | X | 2012-09-18 | DocSubmissions\IORef Set Point Manager CondEntTempReset.docx
IORef | Heejin Cho | 2012-09-13 | X | 2012-09-18 | DocSubmissions\IORef Set Point Manager IdealCondEntTempReset.docx
IORef | Simon Vidanovic | 2012-09-17 | X | 2012-09-18 | DocSubmissions\InputOutputReference_BSDF rev1.docx | WindowMaterial:Gas only
IORef | Thierry Noudui | 2012-09-17 | X | 2012-09-18 | DocSubmissions\InputOutputReferenceUpdate.docx | Continues to send entire document without tracked changes.
IORef | Chandan Sharma | 2012-09-18 | X | 2012-09-18 | DocSubmissions\IORef_SPManager Simulation Order_18 Sep 2012.docx
IORef | Mike Witte | 2012-09-18 | X | 2012-09-24 | DocSubmissions\InputOutputReference-Ticket6408-Multipliers-MJW-2012-09-18b.docx
IORef | Linda Lawrie | 2012-09-19 | X | 2012-09-19 |  | Updating autosize tables
IORef | Brent Griffith | 2012-09-19 | X | 2012-09-24 | DocSubmissions\IO_Ref_CR8983.docx
IORef | Rich Raustad | 2012-09-21 | X | 2012-09-24 | DocSubmissions\IORef_GroupWaterSystems_19Sep2012.docx
IORef | Linda Lawrie | 2012-09-21 | X | 2012-09-24 |  | Need some changes due to CR8883.
IORef | Mike Witte | 2012-09-23 | X | 2012-09-24 | DocSubmissions\InputOutputReference-HVACTemplate-MJW-2012-09-24.docx
IORef | Simon Vidanovic | 2012-09-27 | X | 2012-09-27 | DocSubmissions\OutputDetailsAndExamples.docx | for complex windows.
Output Details | Jason Glazer | 2012-09-06 | X | 2012-09-12 | DocSubmissions\OutputDetailsAndExamples-LightingSummary.docx
Output Details | Therese Stovall | 2012-09-10 | X | 2012-09-12 | DocSubmissions\refrigerantsOnlyOutputDetailsAndExamples.docx | removed footnotes from this document. References should be in the descriptions of the datasets.
Output Details | Bereket Nigusse | 2012-09-12 | X | 2012-09-12 | DocSubmissions\OutputDetailsAndExamples_CR8797_31July2012.docx
Programming Standard | Brent Griffith | 2012-06-19 | X | 2012-09-12 | DocSubmissions\ProgrammingStandard_libraryPolicy.docx
Programming Standard | Brent Griffith | 2012-09-12 | X | 2012-09-25 | DocSubmissions\ProgrammingStandard_BGedits_9-13.docx
Tips & Tricks | Mike Witte | 2012-09-18 | X | 2012-09-25 | DocSubmissions\Tips_and_Tricks_Using_EnergyPlus-Ticket6408Multipliers-MJW-2012-09-18.docx
Mod Dev Guide | Noel Keen | 2011-10-10 |  |  | DocSubmissions\EP_compile_with_Makefile.docx | not in V7 doc release.
Mod Dev Guide | Linda Lawrie |  |  |  |  | need to document new "if def" preprocessor elements for compillng
Z_Last Entry (add rows above for conditional formatting)
Note on E1: Linda Lawrie: X=superceded by later submissions

## Doc_CRs
Open/New CRs as of May 2, 2012
Document Category | CR Number | Synopsis | Type | Status (Green background -- submitted or fixed) | Responsibility | Description
Documentation | 8672 | Add definitions of shade report surface types to the Engineering Ref and maybe Output Details | Suggestion | Fixed | Linda Lawrie
Documentation | 8731 | Old syntax lurking in Output Details and Examples | Defect | Fixed | Linda Lawrie
Module Dev Guide | 8457 | Suggest including some guidelines on compiling EnergyPlus | Suggestion | New | Linda Lawrie
Documentation | 8733 | Incorrect and old object names in docs "Coil:DX:..." | Defect | Fixed | Linda Lawrie
| 8089 | Match IO Reference groups/organization to IDD \Group... for \group Node-Branch Management and \group Air Distribution | Defect-Do Not Publish | New | Mike Witte
| 8266 | Add a section on DOAS to tips and tricks and maybe some stuff in I/O ref | Suggestion | New | Mike Witte
| 8320 | Update Getting Started - use training workshop examples | Defect-Do Not Publish | New | Mike Witte
| 8599 | Engineering Ref lacks equations showing how thermal visible and solar absorptances get used | Defect | New | Mike Witte
| 8662 | Clarify the Fan Power input for cooling towers | Suggestion | New | Mike Witte
| 8673 | Tips and Tricks "Air wall, Open air connection between zones" needs updating | Suggestion | New | Mike Witte
| 8682 | Clarify documenation regarding relative coordinates, and Building surface dimensions/thickness | Defect | New | Mike Witte
| 8695 | Shortwave from Lights uses surface material solar absorptance rather than visible absorptance in heat balance calcs. | Defect | New | Mike Witte
| 8758 | Input Output Reference for UtilityCost:Tariff needs more text about meters for on-site power generation plus other things | Defect | New | Mike Witte
Engineering Documentation | 6257 | No documentation on Desiccant Dehumidifier group objects in Eng Ref. | Defect | New | Mike Witte
Tips & Tricks? | 8056 | Add additional documentation on boilers, boiler types | Defect | New | Mike Witte
| 8220 | Thermal Comfort Models (Fanger, Pierce, ..) need documentation update, and equation review. The equations in the code are different from the current documentation. | Defect-Do Not Publish | New | Rick Strand
| 8608 | ZoneHVAC:OutdoorAirUnit figure art needs updating | Defect | New | Rick Strand
| 8678 | Review and update soil properties in Eng Ref and other docs | Suggestion | New | Rick Strand
| 8696 | Update MRT section in Engineering Ref | Defect | New | Rick Strand
| 8744 | ZoneHVAC:LowTemperatureRadiant:ConstantFlow Pump Flow Rate Schedule Name - clarify this is a multiplier | Defect | New | Rick Strand
Documentation | 8222 | The IO reference documentation lacks description or explanation regarding the PMV and PPD variables calculations and the two levels of reporting (comfort reporting and comfort control) available. | Defect-Do Not Publish | New | Rick Strand
| 8119 | Output:Meter I/O ref content does not discuss special meters from electric load center (eg. ElectricityNet:Facility). | Defect | New | Brent Griffith
| 8140 | clean up Eng Ref, Window calculations | Defect-Do Not Publish | New | Brent Griffith
| 8606 | Common pipe documentation needs revision | Defect | New | Brent Griffith
| 8826 | I/O Ref Generator:photovoltaic - Number of modules fields not clear for series/parallel | Defect | New | Brent Griffith
Documentation | 8191 | WaterSystems end use key missing in IO Ref | Defect | New | Brent Griffith
Documentation | 8445 | Missing output variables for WaterUse:Well | Defect | New | Brent Griffith
Documentation | 8652 | ConvergenceLimits changes not documented | Defect | New | Brent Griffith
Documentation (and code) | 8444 | WaterUse:Storage - incorrect code and documentation (code corrected - 10/9/2011) | Defect-Do Not Publish | New | Brent Griffith
| 8550 | IORef documentation - Water to Air HP | Defect | New | Edwin Lee
| 8114 | Engineering documentation for ground heat transfer programs is missing | Suggestion | New | Neal Kruis

## PsychRoutineNameChanges
Old Name | New Name
rhoairfn | PsyRhoAirFnPbTdbW
cpairfn | PsyCpAirFnWTdb
hfgairfn | PsyHfgAirFnWTdb
hgairfn | PsyHgAirFnWTdb
PSYDPT | PsyTdpFnTdbTwbPb
PSYDPW | PsyTdpFnWPb
PSYHTW | PsyHFnTdbW
PSYHTR | PsyHFnTdbRhPb
PSYTHW | PsyTdbFnHW
PsyRhovRH | PsyRhovFnTdbRh
PsyRhovW | PsyRhovFnTdbWPb
PsyRHV | PsyRhFnTdbRhov
PSYRHT | PsyRhFnTdbWPb
PSYTWD | PsyTwbFnTdbWPb
PSYVTW | PsyVFnTdbWPb
PSYWDP | PsyWFnTdpPb
PSYWTH | PsyWFnTdbH
PSYWTP | PsyWFnTdbTwbPb
PSYWTR | PsyWFnTdbRhPb
SATUTH | PsyTsatFnHPb
SatPress | PsyPsatFnTdb
SatTemp | PsyTsatFnPb
CPCW | CPCW
CPHW | CPHW
CVHW | CVHW